## Dashboard
Local Scriptorium MVP Dashboard
Metric | Value | Notes
Total tickets | 44 | MVP backlog items
Total story points | 111 | Relative effort + uncertainty
Total estimate hours | 72.25 | At 6h/week this is about 12 weeks
Planned weekly capacity | 6 | Change this in Sprint Capacity if needed
Approx weeks at 6h/week | 12.0417 | Formula-based rough estimate
Phase | Points | Hours
Phase 0 Setup | 5 | 3
Phase 1 Local Inference | 13 | 7.5
Phase 2 Source Corpus | 16 | 10.75
Phase 3 Manual RAG | 10 | 6
Phase 4 Basic Retrieval | 11 | 7
Phase 5 Grounded Answers | 14 | 9
Phase 6 Evaluation | 17 | 12
Phase 7 QVAC Spike | 8 | 5
Phase 8 Portfolio | 17 | 12

## Backlog
Key | Summary | Issue Type | Epic | Component | Story Points | Estimate Hours | Original Estimate | Priority | Labels | Target Sprint | Due Date | Energy Level | Status | Description
LS-1 | Create project charter | Task | Project Setup | Phase 0 Setup | 1 | 0.75 | 2700 | High | setup | Sprint 0 | 2026-05-17 | Low | Backlog | Goal: Define the mission, MVP goal, non-goals, success criteria, constraints, and completion definition. Acceptance Criteria: - Project charter exists in docs/project_charter.md - MVP and non-goals are explicit - Success criteria are testable Output Artifact: docs/project_charter.md
LS-2 | Create Jira Scrum-lite project | Task | Project Setup | Phase 0 Setup | 1 | 0.75 | 2700 | High | setup | Sprint 0 | 2026-05-17 | Low | Backlog | Goal: Create the Jira project and import this MVP backlog. Acceptance Criteria: - Project named Local Scriptorium exists - Board has Backlog, Selected for Sprint, In Progress, Blocked, Review, Done - Story points and original estimate are visible Output Artifact: Jira board URL or screenshot
LS-3 | Create repo and folder structure | Task | Project Setup | Phase 0 Setup | 1 | 0.5 | 1800 | High | setup | Sprint 0 | 2026-05-17 | Low | Backlog | Goal: Create a simple project workspace with folders for sources, chunks, outputs, evals, docs, decisions, and scripts. Acceptance Criteria: - Folder structure exists - README stub exists - No extra framework added yet Output Artifact: Repo/folder screenshot or README
LS-4 | Create decision log template | Task | Project Setup | Phase 0 Setup | 1 | 0.5 | 1800 | Medium | setup | Sprint 0 | 2026-05-17 | Low | Backlog | Goal: Create a reusable decision log for technical and product decisions. Acceptance Criteria: - decision_log.md exists - Template includes date, context, options, decision, reason, consequences - First decision recorded Output Artifact: decisions/decision_log.md
LS-5 | Validate imported Jira backlog | Task | Project Setup | Phase 0 Setup | 1 | 0.5 | 1800 | Medium | setup | Sprint 0 | 2026-05-17 | Low | Backlog | Goal: Confirm the imported backlog is usable and estimates are visible. Acceptance Criteria: - CSV import completed - Ticket descriptions preserved - Estimates mapped or documented as custom fields Output Artifact: Screenshot or short setup note
LS-6 | Install Ollama | Task | Local Inference Baseline | Phase 1 Local Inference | 2 | 1 | 3600 | High | ollama | Sprint 1 | 2026-05-24 | Medium | Backlog | Goal: Install Ollama locally as the easiest baseline for local inference. Acceptance Criteria: - Ollama installed - Terminal command works - Install notes saved Output Artifact: docs/setup_notes.md
LS-7 | Run first local model | Task | Local Inference Baseline | Phase 1 Local Inference | 2 | 1 | 3600 | High | local-inference | Sprint 1 | 2026-05-24 | Medium | Backlog | Goal: Run a small local LLM and produce the first local answer. Acceptance Criteria: - Model pulled - Prompt returns output - Model name and command saved Output Artifact: outputs/local_model_hello_world.md
LS-8 | Create 10 baseline prompts | Task | Local Inference Baseline | Phase 1 Local Inference | 2 | 1 | 3600 | Medium | evals | Sprint 1 | 2026-05-24 | Medium | Backlog | Goal: Create a small prompt set for comparing local and cloud answers. Acceptance Criteria: - 10 prompts written - Prompts cover summary, argument extraction, evidence, uncertainty, and refusal - Prompts saved in evals folder Output Artifact: evals/baseline_prompts.md
LS-9 | Save 10 baseline local outputs | Task | Local Inference Baseline | Phase 1 Local Inference | 2 | 1.5 | 5400 | High | local-inference | Sprint 1 | 2026-05-24 | Medium | Backlog | Goal: Run the baseline prompts through the local model and save outputs. Acceptance Criteria: - All 10 prompts run locally - Outputs saved with model name and date - Obvious failures noted Output Artifact: outputs/baseline_local_outputs.md
LS-10 | Compare local output vs ChatGPT | Task | Local Inference Baseline | Phase 1 Local Inference | 3 | 2 | 7200 | High | evals | Sprint 1 | 2026-05-24 | High | Backlog | Goal: Run the same prompts through ChatGPT and compare quality, latency, and structure. Acceptance Criteria: - Same prompt set used - Local vs cloud differences recorded - At least 3 failure examples captured Output Artifact: docs/local_vs_cloud_comparison.md
LS-11 | Write local inference baseline memo | Task | Local Inference Baseline | Phase 1 Local Inference | 2 | 1 | 3600 | High | docs | Sprint 1 | 2026-05-24 | Medium | Backlog | Goal: Summarize what local inference means in practice after first hands-on testing. Acceptance Criteria: - Memo explains what worked - Memo explains what failed - Memo identifies next smallest step Output Artifact: docs/day_1_local_inference_baseline.md
LS-12 | Select first source corpus | Task | Source Corpus and Chunking | Phase 2 Source Corpus | 1 | 0.75 | 2700 | High | ingestion | Sprint 2 | 2026-05-31 | Low | Backlog | Goal: Choose the first 3 to 5 clean text sources for the MVP corpus. Acceptance Criteria: - 3 to 5 sources selected - Sources are text or markdown - Copyright/privacy status noted Output Artifact: sources/source_selection.md
LS-13 | Create source metadata file | Task | Source Corpus and Chunking | Phase 2 Source Corpus | 2 | 1 | 3600 | High | ingestion | Sprint 2 | 2026-05-31 | Low | Backlog | Goal: Create metadata for each source so chunks can be traced back later. Acceptance Criteria: - Metadata includes source_id, title, author, type, notes - Every source has a stable ID - File saved in sources folder Output Artifact: sources/sources_metadata.csv
LS-14 | Clean first 3 source files | Task | Source Corpus and Chunking | Phase 2 Source Corpus | 3 | 2 | 7200 | High | ingestion | Sprint 2 | 2026-05-31 | Medium | Backlog | Goal: Prepare source files by removing obvious formatting junk and making text usable. Acceptance Criteria: - 3 files cleaned - Headings preserved where useful - Cleaned files saved separately Output Artifact: sources/clean/
LS-15 | Define chunk ID convention | Task | Source Corpus and Chunking | Phase 2 Source Corpus | 1 | 0.5 | 1800 | High | chunking | Sprint 2 | 2026-05-31 | Low | Backlog | Goal: Create a stable ID convention for chunks. Acceptance Criteria: - Convention documented - Example chunk IDs included - IDs encode source and sequence Output Artifact: docs/chunking_rules.md
LS-16 | Create initial manual chunks | Task | Source Corpus and Chunking | Phase 2 Source Corpus | 2 | 1.5 | 5400 | High | chunking | Sprint 2 | 2026-05-31 | Medium | Backlog | Goal: Manually chunk one source to understand the desired structure before scripting. Acceptance Criteria: - At least 20 chunks created - Each chunk has source ID - Chunks are readable and not overly tiny Output Artifact: chunks/manual_chunks.md
LS-17 | Create chunking script with AI coding tool | Task | Source Corpus and Chunking | Phase 2 Source Corpus | 5 | 4 | 14400 | High | chunking | Sprint 3 | 2026-06-07 | High | Backlog | Goal: Use an AI coding assistant to create a simple script that chunks txt and markdown files. Acceptance Criteria: - Script reads sources folder - Script writes chunks.json - Script preserves source filename and source ID - Script prints chunk count Output Artifact: scripts/chunk_sources.py and chunks/chunks.json
LS-18 | Validate chunk output | Task | Source Corpus and Chunking | Phase 2 Source Corpus | 2 | 1 | 3600 | High | chunking | Sprint 3 | 2026-06-07 | Medium | Backlog | Goal: Check that automated chunks are coherent and traceable. Acceptance Criteria: - 10 random chunks inspected - Bad chunk examples logged - Chunking rules updated if needed Output Artifact: docs/chunk_validation_notes.md
LS-19 | Create 10 manual RAG questions | Task | Manual RAG | Phase 3 Manual RAG | 2 | 1 | 3600 | High | rag | Sprint 3 | 2026-06-07 | Medium | Backlog | Goal: Create questions that require source-grounded answers. Acceptance Criteria: - 10 questions written - Questions include factual, interpretive, and comparison types - Expected source hints added where possible Output Artifact: evals/manual_rag_questions.md
LS-20 | Manually select relevant chunks | Task | Manual RAG | Phase 3 Manual RAG | 2 | 1 | 3600 | High | rag | Sprint 3 | 2026-06-07 | Medium | Backlog | Goal: Pick source chunks by hand for each manual RAG question. Acceptance Criteria: - Each question has selected chunk IDs - Selection rationale noted - At least one insufficient-evidence case included Output Artifact: evals/manual_rag_contexts.md
LS-21 | Run prompts with and without chunks | Task | Manual RAG | Phase 3 Manual RAG | 3 | 2 | 7200 | High | rag | Sprint 4 | 2026-06-14 | High | Backlog | Goal: Compare local answers with and without supplied context. Acceptance Criteria: - All 10 questions run both ways - Outputs saved - Differences highlighted Output Artifact: outputs/manual_rag_comparison.md
LS-22 | Document grounding improvements and failures | Task | Manual RAG | Phase 3 Manual RAG | 3 | 2 | 7200 | High | docs | Sprint 4 | 2026-06-14 | High | Backlog | Goal: Write what manual RAG improved and where it still failed. Acceptance Criteria: - At least 3 improvements documented - At least 3 failures documented - Decision made on retrieval approach for MVP Output Artifact: docs/manual_rag_findings.md
LS-23 | Build keyword search over chunks | Task | Basic Retrieval | Phase 4 Basic Retrieval | 3 | 2 | 7200 | High | retrieval | Sprint 4 | 2026-06-14 | High | Backlog | Goal: Create a simple retrieval baseline using keyword or lexical search. Acceptance Criteria: - Script accepts a question - Script searches chunks.json - Script returns candidate chunks Output Artifact: scripts/search_chunks.py
LS-24 | Return top 5 chunks for a question | Story | Basic Retrieval | Phase 4 Basic Retrieval | 3 | 2 | 7200 | High | retrieval | Sprint 5 | 2026-06-21 | High | Backlog | Goal: As a user, I can ask a question and see the top 5 retrieved source chunks. Acceptance Criteria: - Question input supported - Top 5 chunks displayed with source IDs - Output is readable Output Artifact: outputs/sample_retrieval_output.md
LS-25 | Log retrieved chunks to output file | Task | Basic Retrieval | Phase 4 Basic Retrieval | 2 | 1 | 3600 | Medium | retrieval | Sprint 5 | 2026-06-21 | Medium | Backlog | Goal: Save retrieval results so they can be evaluated later. Acceptance Criteria: - Results saved to outputs folder - Includes question, timestamp, chunk IDs, scores if available - File format is reusable Output Artifact: outputs/retrieval_log.json or md
LS-26 | Test retrieval on 15 questions | Task | Basic Retrieval | Phase 4 Basic Retrieval | 3 | 2 | 7200 | High | evals | Sprint 5 | 2026-06-21 | High | Backlog | Goal: Run retrieval on a broader set of questions and inspect quality. Acceptance Criteria: - 15 questions tested - Correct/incorrect retrieval noted - Failure examples saved Output Artifact: evals/retrieval_test_results.md
LS-27 | Create grounded answer prompt template | Task | Grounded Answer Generator | Phase 5 Grounded Answers | 2 | 1 | 3600 | High | rag | Sprint 5 | 2026-06-21 | Medium | Backlog | Goal: Create the strict prompt template that forces sourced, cautious answers. Acceptance Criteria: - Template says use only provided sources - Template requires source IDs - Template includes uncertainty and insufficient evidence section Output Artifact: docs/grounded_answer_prompt.md
LS-28 | Connect retrieval output to model input | Story | Grounded Answer Generator | Phase 5 Grounded Answers | 5 | 4 | 14400 | High | rag | Sprint 6 | 2026-06-28 | High | Backlog | Goal: As a user, retrieved chunks are passed into the local model as answer context. Acceptance Criteria: - Retrieval output becomes model context - Prompt template applied - Command documented Output Artifact: scripts/answer_with_context.py
LS-29 | Generate grounded answer with source IDs | Story | Grounded Answer Generator | Phase 5 Grounded Answers | 3 | 2 | 7200 | High | rag | Sprint 6 | 2026-06-28 | High | Backlog | Goal: As a user, I receive an answer that cites the source chunks it used. Acceptance Criteria: - Answer includes source IDs - Answer is based on retrieved chunks - Output saved Output Artifact: outputs/sample_grounded_answer.md
LS-30 | Add uncertainty and insufficient evidence section | Task | Grounded Answer Generator | Phase 5 Grounded Answers | 2 | 1 | 3600 | High | rag | Sprint 6 | 2026-06-28 | Medium | Backlog | Goal: Make the model explicitly state uncertainty and source limitations. Acceptance Criteria: - Output includes uncertainty section - Output includes what sources do not establish - At least one refusal/insufficient evidence example tested Output Artifact: outputs/insufficient_evidence_example.md
LS-31 | Save generated answers to outputs folder | Task | Grounded Answer Generator | Phase 5 Grounded Answers | 2 | 1 | 3600 | Medium | rag | Sprint 6 | 2026-06-28 | Medium | Backlog | Goal: Ensure generated answers are saved consistently for review and case study evidence. Acceptance Criteria: - File naming convention exists - Question, sources, model, and answer are saved - At least 5 sample answers saved Output Artifact: outputs/grounded_answers/
LS-32 | Create 20 question MVP eval set | Task | Mini Evaluation | Phase 6 Evaluation | 5 | 4 | 14400 | High | evals | Sprint 7 | 2026-07-05 | High | Backlog | Goal: Create a compact evaluation set for MVP quality testing. Acceptance Criteria: - 20 questions created - Expected answer traits included - Questions cover factual, interpretive, comparison, and insufficient evidence cases Output Artifact: evals/mvp_eval_set.csv
LS-33 | Define scoring rubric | Task | Mini Evaluation | Phase 6 Evaluation | 3 | 2 | 7200 | High | evals | Sprint 7 | 2026-07-05 | Medium | Backlog | Goal: Define how outputs will be judged. Acceptance Criteria: - Rubric includes retrieval correctness - Rubric includes hallucination/unsupported claim check - Rubric includes usefulness score Output Artifact: evals/scoring_rubric.md
LS-34 | Run mini eval local only vs local RAG | Task | Mini Evaluation | Phase 6 Evaluation | 3 | 2 | 7200 | High | evals | Sprint 7 | 2026-07-05 | High | Backlog | Goal: Compare local model answers with and without retrieval. Acceptance Criteria: - Same questions run in both modes - Scores recorded - At least 5 failures inspected Output Artifact: evals/mvp_eval_results.csv
LS-35 | Write failure taxonomy | Task | Mini Evaluation | Phase 6 Evaluation | 3 | 2 | 7200 | High | evals | Sprint 8 | 2026-07-12 | Medium | Backlog | Goal: Categorize the failure modes seen during evaluation. Acceptance Criteria: - Failure categories defined - Examples included - Mitigations proposed Output Artifact: docs/failure_taxonomy.md
LS-36 | Summarize MVP eval findings | Task | Mini Evaluation | Phase 6 Evaluation | 3 | 2 | 7200 | High | docs | Sprint 8 | 2026-07-12 | Medium | Backlog | Goal: Write a concise eval report that can be used in the portfolio case study. Acceptance Criteria: - Summary includes what worked - Summary includes what failed - Summary includes next improvements Output Artifact: docs/mvp_eval_summary.md
LS-37 | Install QVAC SDK | Spike | QVAC Spike | Phase 7 QVAC Spike | 3 | 2 | 7200 | Medium | qvac | Sprint 8 | 2026-07-12 | High | Backlog | Goal: Attempt to install Tether's QVAC SDK and document setup. Acceptance Criteria: - Installation attempted - Commands captured - Blockers documented if install fails Output Artifact: docs/qvac_setup_notes.md
LS-38 | Run QVAC hello world or capture blocker | Spike | QVAC Spike | Phase 7 QVAC Spike | 3 | 2 | 7200 | Medium | qvac | Sprint 8 | 2026-07-12 | High | Backlog | Goal: Try a minimal local completion with QVAC or capture why it could not run. Acceptance Criteria: - Hello-world completion attempted - Output saved or blocker documented - No MVP dependency created Output Artifact: outputs/qvac_hello_world.md or docs/qvac_blockers.md
LS-39 | Write QVAC vs Ollama comparison memo | Task | QVAC Spike | Phase 7 QVAC Spike | 2 | 1 | 3600 | Medium | qvac | Sprint 8 | 2026-07-12 | Medium | Backlog | Goal: Compare QVAC and Ollama from an implementation/product perspective. Acceptance Criteria: - Setup difficulty compared - Developer experience compared - Recommendation for MVP+1 recorded Output Artifact: docs/qvac_vs_ollama.md
LS-40 | Write product brief | Task | Portfolio Package | Phase 8 Portfolio | 3 | 2 | 7200 | High | portfolio | Sprint 9 | 2026-07-19 | Medium | Backlog | Goal: Create a concise product brief for Local Scriptorium. Acceptance Criteria: - Problem, user, use cases, non-goals, success metrics included - Brief understandable to nontechnical reader - Limitations stated Output Artifact: docs/product_brief.md
LS-41 | Create architecture diagram | Task | Portfolio Package | Phase 8 Portfolio | 3 | 2 | 7200 | High | portfolio | Sprint 9 | 2026-07-19 | Medium | Backlog | Goal: Create a simple architecture diagram showing data flow and local/cloud boundaries. Acceptance Criteria: - Diagram shows sources, chunking, retrieval, local model, output, eval - Local boundary is explicit - Diagram included in README or docs Output Artifact: docs/architecture_diagram.png or md
LS-42 | Create risk register | Task | Portfolio Package | Phase 8 Portfolio | 3 | 2 | 7200 | High | risk | Sprint 9 | 2026-07-19 | Medium | Backlog | Goal: Document implementation and product risks. Acceptance Criteria: - At least 8 risks listed - Each risk has mitigation - Privacy, hallucination, retrieval, and hardware constraints included Output Artifact: docs/risk_register.md
LS-43 | Write README case study | Task | Portfolio Package | Phase 8 Portfolio | 5 | 4 | 14400 | High | portfolio | Sprint 9 | 2026-07-19 | High | Backlog | Goal: Write the main portfolio case study. Acceptance Criteria: - README explains mission, architecture, demo workflow, eval, failures, and next steps - README avoids overclaiming - README includes sample outputs Output Artifact: README.md
LS-44 | Create final demo script and screenshots | Task | Portfolio Package | Phase 8 Portfolio | 3 | 2 | 7200 | High | portfolio | Sprint 9 | 2026-07-19 | Medium | Backlog | Goal: Prepare a repeatable demo and capture evidence. Acceptance Criteria: - Demo script has exact commands - Screenshots or output examples saved - MVP completion criteria checked Output Artifact: docs/demo_script.md and screenshots

## Roadmap
Phase | Target Sprint | Tickets | Story Points | Estimate Hours | Start Due | End Due | Goal
Phase 0 Setup | Sprint 0 | 5 | 5 | 3 | 2026-05-17 | 2026-05-17 | Project system and importable backlog.
Phase 1 Local Inference | Sprint 1 | 6 | 13 | 7.5 | 2026-05-24 | 2026-05-24 | Run local model and compare with cloud output.
Phase 2 Source Corpus | Sprint 2, Sprint 3 | 7 | 16 | 10.75 | 2026-05-31 | 2026-06-07 | Prepare source files and chunks.
Phase 3 Manual RAG | Sprint 3, Sprint 4 | 4 | 10 | 6 | 2026-06-07 | 2026-06-14 | Understand grounding before automation.
Phase 4 Basic Retrieval | Sprint 4, Sprint 5 | 4 | 11 | 7 | 2026-06-14 | 2026-06-21 | Retrieve relevant chunks automatically.
Phase 5 Grounded Answers | Sprint 5, Sprint 6 | 5 | 14 | 9 | 2026-06-21 | 2026-06-28 | Generate sourced answers from retrieved context.
Phase 6 Evaluation | Sprint 7, Sprint 8 | 5 | 17 | 12 | 2026-07-05 | 2026-07-12 | Measure quality and failure modes.
Phase 7 QVAC Spike | Sprint 8 | 3 | 8 | 5 | 2026-07-12 | 2026-07-12 | Touch Tether's local-first ecosystem without blocking MVP.
Phase 8 Portfolio | Sprint 9 | 5 | 17 | 12 | 2026-07-19 | 2026-07-19 | Turn prototype into job evidence.

## Sprint Capacity
Sprint | Due Date | Tickets | Story Points | Estimate Hours | Capacity Hours | Over Under Hours | Comment
Sprint 0 | 2026-05-17 | 5 | 5 | 3 | 6 | 3
Sprint 1 | 2026-05-24 | 6 | 13 | 7.5 | 6 | -1.5
Sprint 2 | 2026-05-31 | 5 | 9 | 5.75 | 6 | 0.25
Sprint 3 | 2026-06-07 | 4 | 11 | 7 | 6 | -1
Sprint 4 | 2026-06-14 | 3 | 9 | 6 | 6 | 0
Sprint 5 | 2026-06-21 | 4 | 10 | 6 | 6 | 0
Sprint 6 | 2026-06-28 | 4 | 12 | 8 | 6 | -2
Sprint 7 | 2026-07-05 | 3 | 11 | 8 | 6 | -2
Sprint 8 | 2026-07-12 | 5 | 14 | 9 | 6 | -3
Sprint 9 | 2026-07-19 | 5 | 17 | 12 | 6 | -6

## MVP+1 Parking Lot
Key | Summary | Issue Type | Story Points | Estimate Hours | Label | Notes
MVP+1-1 | Add semantic embeddings and vector search | Story | 5 | 4 | semantic-retrieval | Add embeddings after keyword retrieval MVP works.
MVP+1-2 | Compare keyword vs semantic retrieval | Task | 3 | 2 | evals | Run same eval questions through both retrieval methods.
MVP+1-3 | Add simple CLI command | Task | 3 | 2 | cli | Make question answering easier to run without manual script arguments.
MVP+1-4 | Deepen QVAC integration | Spike | 5 | 4 | qvac | Try replacing Ollama path with QVAC where feasible.
MVP+1-5 | Create tiny local UI | Task | 5 | 4 | ui | Only after CLI/core loop works.
MVP+1-6 | AI vendor comparison memo | Task | 3 | 2 | governance | Compare OpenAI, Anthropic, Microsoft, local/Ollama, QVAC.
MVP+1-7 | AI use-case triage template | Task | 3 | 2 | governance | Reusable enterprise intake artifact.

## ReadMe
Local Scriptorium MVP Planning Workbook
Purpose | This workbook is a human-readable planning companion to the Jira CSV import files.
Jira import | Use the CSV files for Jira. This workbook is for review, planning, and roadmap visibility.
Estimate rule | Story points estimate complexity/uncertainty. Original Estimate in Jira CSV is stored in seconds.
MVP goal | source → chunk → retrieve → answer → cite → evaluate
Scope warning | Do not add UI, fine-tuning, OCR, cloud deployment, or hardware purchases before MVP evidence exists.